## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE MEDIQ ADVISOR - MENTAL HEALTH ADVISOR | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE PROF. ANAGHA AHER | [6 empty] | DATE | [6 empty] | 2022-10-11
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [39 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Faizan, Arya, Himanshu, Harshal | 2024-01-06 | 2024-01-20 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Faizan, Arya, Harshal | 2024-01-21 | 2024-01-27 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.3 | Discussing the project topic with the help of paper prototype. | Faizan, Arya, Himanshu, Harshal | 2024-01-28 | 2024-02-03 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
1.4 | Designing the Graphical User Interface(GUI) and Implementation | Faizan, Himanshu | 2024-02-04 | 2024-02-24 | 3 | 100% | bar: WEEK 5 M to WEEK 7 F
1.5 | Presentation I | Faizan, Arya, Himanshu, Harshal | 2024-02-25 | 2024-03-02 | 1 | 100% | bar: WEEK 8 M to WEEK 8 F
2 | Project Design and Implementation
2.1 | Database Design | Arya, Himanshu | 2024-03-03 | 2024-03-09 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2.2 | Database Connectivity of all modules | Himanshu | 2024-03-10 | 2024-03-23 | 2 | 100% | bar: WEEK 10 M to WEEK 11 F
2.3 | Integration of all modules and Report Writing | Arya, Himanshu | 2024-03-24 | 2024-04-06 | 2 | 100% | bar: WEEK 11 M to WEEK 12 F
2.4 | Presentation II | Faizan, Arya, Himanshu, Harshal | 2024-04-07 | 2024-04-13 | 1 | 100% | bar: WEEK 13 M to WEEK 13 F